## Cost Estimate Sheet
COST ESTIMATE FOR IMPLEMENTATION OF EOFFICE AND SPARROW AT STATE/UT
Project Assessment Details | [6 empty] | Select No. of Users from Dropdown |  | For Project Plan and Timelines |  |  | Click Here
No. of eOffice Users in State (Secretariat, District Administration, Departments, Directorates, etc.) | [6 empty] | 1001-5000
No. of SPARROW Users in Organized Services / Cadres | [6 empty] | 1001-5000
S.No. | Costing Head |  |  | Quantity $ | Duration (in months) $ | Estimated Unit Cost (in INR) $ | Total Cost (in INR) |  | $ The Cost for below mentioned items / manpower resources is required to be filled by user department and it will automatically get reflected in the Main Sheet
Requirements at Client Side | [8 empty] | Price of Items / Manpower Resources
1 | Workstations | Desktop |  | 0 | Not Applicable | 49800 | 0 |  | S.No. | Item/Manpower Resource |  | Estimated Unit Cost (in INR)
|  | Laptop |  | 0 |  | 58890 | 0 |  | 1 | Workstations | Desktop [GEM LINK] | 49800
2 | Scanners | Medium End |  | 0 |  | 49800 | 0 |  | 2 |  | Laptop [GEM LINK] | 58890
|  | Multi-Function |  | 0 |  | 12650 | 0 |  | 3 | Scanners | High End [GEM LINK] | 84597
3 | Digital Signature Certificates (DSC) - Two years Certificate validity |  |  | 0 |  | 690 | 0 |  | 4 |  | Medium End [GEM LINK] | 49800
TOTAL# | [6 empty] | 0 |  | 5 |  | Multi-Function [GEM LINK] | 12650
Setting up of Units | [8 empty] | 6 | Digital Signature Certificates (DSC) - Two years Certificate validity [GEM LINK] |  | 690
S.No. | Name of Unit | Costing Head |  | Quantity $ | Duration (in months) $ | Estimated Unit Cost (in INR) $ | Total Cost (in INR)
1 | Digitization, Diary and Dispatch Unit | No. of Pages to be scanned in legacy files (Hiring of Digitization Agency) |  | 0 | Not Applicable |  | 0 |  | 7 | Duration (in Months) for Manpower Resources |  | 36
|  | Workstations | Desktop | 3 |  | 49800 | 149400 |  | 8 | Project Manager |  | 55000
|  |  | Laptop | 0 |  | 58890 | 0 |  | 9 | Project Lead |  | 35000
|  | Scanners | High End | 1 |  | 84597 | 84597 |  | 10 | Project Engineer |  | 25000
|  |  | Medium End | 2 |  | 49800 | 99600 |  | 11 | Technical Manager |  | 70000
|  | Manpower Resources+ | Project Lead | 1 | 36 | 35000 | 1260000 |  | 12 | Deployment Lead |  | 40000
|  |  | Project Engineer | 2 | 36 | 25000 | 1800000 |  | 13 | Deployment Engineer |  | 30000
2 | Capacity Building Unit | Workstations | Desktop | 10 | Not Applicable | 49800 | 498000 |  | For Indicative Work Profile / Skill Set of aforesaid manpower resources |  |  | Click Here
|  |  | Laptop | 1 |  | 58890 | 58890
|  | Scanners | Multi-Function | 1 |  | 12650 | 12650 |  | 14 | Duration (in Months) for Deployment Infrastructure |  | 60
|  | Manpower Resources+ | Project Lead | 1 | 36 | 35000 | 1260000 |  | 15 | SSL Certificate (Applicable for Two Years only) [GEM LINK] |  | 4498
|  |  | Project Engineer | 3 | 36 | 25000 | 2700000 |  | 16 | Workshop (To be organized every year for three consecutive years for One State/UT) |  | 0
3 | Data Management, On-site Support and Helpdesk Unit | Workstations | Desktop | 5 | Not Applicable | 49800 | 249000
|  |  | Laptop | 2 |  | 58890 | 117780 |  | 17 | No. of States/UTs |  | 30
|  | Manpower Resources+ | Project Lead | 3 | 36 | 35000 | 3780000 |  | 18 | Cost towards hiring of Manpower Resources for setting up of Project Management Unit at DAR&PG (Lump sum for all States/UTs) |  | 0
|  |  | Project Engineer | 4 | 36 | 25000 | 3600000
4 | Project Management Unit | Workstations | Desktop | 3 | Not Applicable | 49800 | 149400
|  |  | Laptop | 1 |  | 58890 | 58890 |  | 19 | Contingencies with DAR&PG (Lump sum) |  | 0
|  | Manpower Resources+ | Project Manager | 1 | 36 | 55000 | 1980000
|  |  | Project Lead | 1 | 36 | 35000 | 1260000
|  |  | Project Engineer | 2 | 36 | 25000 | 1800000 |  | SUMMARY SHEET
5 | System Administration % | Workstations | Desktop | 3 | Not Applicable | 49800 | 149400 |  | S.No. | Description |  | Quantity | Total Cost For One State/UT (in INR) | Total Cost For All States/UTs (in INR) | Total Cost For All States/UTs for 1st Year (in INR) | Total Cost For All States/UTs for 2nd Year (in INR) | Total Cost For All States/UTs for 3rd Year (in INR) | Cost to be submitted to
|  |  | Laptop | 1 |  | 58890 | 58890
|  | Manpower Resources+ | Technical Manager | 1 | 36 | 70000 | 2520000
|  |  | Deployment Lead | 1 | 36 | 40000 | 1440000 |  | 1 | Workstations | Desktop | 24 | 1195200 | 35856000 | 35856000 | 0 | 0 | State/UT
|  |  | Deployment Engineer | 2 | 36 | 30000 | 2160000 |  |  |  | Laptop | 5 | 294450 | 8833500 | 8833500 | 0 | 0
TOTAL# | [6 empty] | 27246497 |  | 2 | Scanners | High End | 1 | 84597 | 2537910 | 2537910 | 0 | 0 | State/UT
Requirements at DAR&PG | [10 empty] | Medium End | 2 | 99600 | 2988000 | 2988000 | 0 | 0
S.No. | Costing Head | [5 empty] | Total Cost (in INR) |  |  |  | Multi-Function | 1 | 12650 | 379500 | 379500 | 0 | 0
1 | Workshop (To be organized every year for three consecutive years for One State/UT) | [5 empty] | 0 |  | TOTAL COST (Procurement of Workstations and Scanners) |  |  |  | 1686497 | 50594910 | 50594910 | 0 | 0
Note: Manpower Resources for Project Management Unit to be setup at DAR&PG and Contingencies will be separately calculated once the requirement from respective state will be received | [8 empty] | 3 | eOffice Procurement Cost |  | N/A | 3850000 | 115500000 | 115500000 | 0 | 0 | NICSI
[9 empty] | 4 | SPARROW Procurement Cost |  |  | 3850000 | 115500000 | 115500000 | 0 | 0
TOTAL# | [6 empty] | 0 |  | TOTAL COST (Procurement of eOffice and SPARROW) |  |  |  | 7700000 | 231000000 | 231000000 | 0 | 0
eOffice & SPARROW Procurement Cost (Applicable for Five Years) | [8 empty] | 5 | eOffice Deployment Infrastructure Cost |  | N/A | 31519500 | 945585000 | 945585000 | 0 | 0 | NICSI (in case hosted at NDC-BBSR)
1 | eOffice | Product Enhancement and Maintenance Cost |  |  |  |  | 2200000 |  | 6 | SPARROW Deployment Infrastructure Cost |  |  | 22818780 | 684563400 | 684563400 | 0 | 0
|  | Operations and Core Roll Out Components Cost |  |  |  |  | 1650000 |  | TOTAL COST (Procurement of Deployment Infrastructure) |  |  |  | 54338280 | 1630148400 | 1630148400 | 0 | 0
2 | SPARROW | Product Enhancement and Maintenance Cost |  |  |  |  | 2200000 |  | 7 | Manpower Resources+ | Project Manager | 1 | 1980000 | 59400000 | 19800000 | 19800000 | 19800000 | NICSI
|  | Operations and Core Roll Out Components Cost |  |  |  |  | 1650000 |  |  |  | Project Lead | 6 | 7560000 | 226800000 | 75600000 | 75600000 | 75600000
TOTAL* | [6 empty] | 7700000 |  |  |  | Project Engineer | 11 | 9900000 | 297000000 | 99000000 | 99000000 | 99000000
Deployment Infrastructure Cost | [10 empty] | Technical Manager | 1 | 2520000 | 75600000 | 25200000 | 25200000 | 25200000
Costing Head | [6 empty] | Total Cost (in INR) |  |  |  | Deployment Lead | 1 | 1440000 | 43200000 | 14400000 | 14400000 | 14400000
[7 empty] | Duration (in Months) | 60 |  |  | Deployment Engineer | 2 | 2160000 | 64800000 | 21600000 | 21600000 | 21600000
1 | Deployment Infrastructure Cost - eOffice @ |  |  | Cost for One Month |  | 525325 | 31519500 |  | TOTAL COST (Hiring of Manpower Resources for various units) |  |  | 22 | 25560000 | 766800000 | 255600000 | 255600000 | 255600000
2 | Deployment Infrastructure Cost - SPARROW @ |  |  | Cost for One Month |  | 380313 | 22818780 |  | 8 | Digital Signature Certificates (DSC) - Two years Certificate validity |  | 0 | 0 | 0 | 0 | 0 |  | State/UT
3 | eSign facility ^ | [5 empty] | 0
4 | SSL Certificate for both eOffice & SPARROW instance ^ (Applicable for Two Years only | [5 empty] | 8996 |  | 9 | SSL Certificate for both eOffice & SPARROW instance (Applicable for Two Years only) |  | 2 | 8996 | 269880 | 269880 | 0 |  | State/UT
5 | DNS Registration for both eOffice & SPARROW instance ^ (FREE in case DNS is registered in .nic.in or .gov.in domain) | [5 empty] | 0
6 | SMS & Email Gateway ^ | [5 empty] | 0 |  | 10 | eSign facility |  | N/A | 0 | 0 | 0 |  |  | State/UT
TOTAL* | [6 empty] | 54347276 |  | 11 | DNS Registration for both eOffice & SPARROW instance |  | N/A | 0 | 0 | 0 |  |  | State/UT
GRAND TOTAL FOR ONE STATE/UT* | [6 empty] | 89293773 |  | 12 | SMS & Email Gateway |  | N/A | 0 | 0 | 0 |  |  | State/UT
GRAND TOTAL FOR ALL STATES/UTs* | [6 empty] | 2678813190 |  | 13 | Hiring of Digitization Agency |  | N/A | 0 | 0 | 0 | 0 | 0 | State/UT
[9 empty] | 14 | Workshop (To be organized every year for three consecutive years for One State/UT) |  | N/A | 0 | 0 | 0 | 0 | 0 | DAR&PG
May kindly note following points: | [8 empty] | 15 | Cost towards hiring of Manpower Resources for Project Management Unit to be setup at DAR&PG (Lump sum for all States/UTs) |  | N/A | N/A | 0 | 0 | 0 | 0 | DAR&PG
Columns highlighted with Yellow Background colour needs to be filled manually.
# | The cost towards "Requirements at Client Side" and "Setting up of Units" needs to be calculated by user department depending upon their local needs, geographical locations, etc. on their own.
[9 empty] | 16 | Contingencies with DAR&PG (Lump sum) |  | N/A | N/A | 0 | 0 | 0 | 0 | DAR&PG
* | The cost is exclusive of applicable taxes and all other charges. | [7 empty] | GRAND TOTAL* |  |  |  | 89293773 | 2678813190 | 2167613190 | 255600000 | 255600000
The final cost will be mentioned in Proforma Invoice (PI) & Project Proposal that will be issued by NICSI to user department.
$ | To be filled by user department as per the actuals and depending upon their local needs, geographical locations, etc. The Cost for Manpower resource is only indicative and Final cost will be mentioned in PI issued by NICSI/GeM/Any other Agency.
@ | The "Deployment Infrastructure Cost - eOffice" and "Deployment Infrastructure Cost - SPARROW" has been calculated based on approved Cloud Rates which are applicable whenever eOffice and SPARROW Product are hosted either in eOffice Cloud at National Data Centre, Shastri Park (NDC-SP) or National Data Centre, Bhubaneswar (NDC-BBSR). Whenever, eOffice and SPARROW Product are hosted outside eOffice Cloud at NDC-SP or NDC-BBSR, the cost towards "Deployment Infrastructure Cost - eOffice" and "Deployment Infrastructure Cost - SPARROW" needs to be borne / calculated by user department on their own.
^ | Whenever the eOffice and SPARROW Product are hosted in eOffice Cloud at NDC-SP; eSign facility, SSL Certificate, DNS Registration and SMS & Email Gateway will be provisioned by NIC. However, the cost for all the aforesaid activities needs to be borne / calculated by user department on their own whenever eOffice and SPARROW Product are hosted outside eOffice Cloud at NDC-SP.
% | Whenever the eOffice and SPARROW Product are hosted in eOffice Cloud at NDC-SP; the cost towards "System Administration" is Nil.
+ | The figures provided above are only general and indicative figures w.r.t. deployment of manpower at a single location that may help user department to estimate their resources, however, it is suggested that user department may also further estimate the requirements based on their local needs / geographical locations etc.
Note on O27: Total Expenditure towards workshop for all the three years needs to be filled here.
Note on U49: In case eOffice and SPARROW instance are hosted at State Data Centre (SDC) or Any other data centre / cloud environment, then in that case, the cost will be provided to State/UT for further transfer to Hosting Service Provider.
Note on U52: In case State/UT hire manpower resources from any other agency (except from NICSI), then in that case, the cost will be provided to State/UT for further transfer to Manpower Services Provider.
Note on T59: In 3rd year, the validity of certificate in DSC gets expired and it needs to be renewed, cost for which is to be borne separately.
Note on T61: In 3rd year, the validity of SSL certificate gets expired and it needs to be renewed, cost for which is to be borne separately.
Note on U63: The cost will be provided to State/UT for further transfer to eSign Service Provider.
Note on U64: DNS Registration will be FREE whenever registered in '.nic.in' and '.gov.in' domain.

## Project Plan & Timelines
PROJECT PLAN FOR IMPLEMENTATION OF EOFFICE AT USER DEPARTMENT (The timelines in project plan have been prepared assuming 5000 users in User Department at One Location)
PHASE I: PLANNING
S.No. | Activities | Purpose | Pre-cursor Activities | Responsibility | Start Date | End Date | Fill Start Date | End Date
1 | Kick-off meeting | To discuss: a) Introduction to eOffice b) Activities Involved in implementation of eOffice c) Implementation Plan and Strategy |  | User Department | T0 | T0 | 2019-10-10 | 2019-10-10
2 | Governance Structure Constitution | To ensure an effective implementation of eOffice, it must be driven & monitored by a well defined Governance structure. The Governance structure includes the following: a) Project Steering Committee b) Department Nodal Officer c) Nodal Coordinators d) Project Implementation Committee |  | User Department | T0 | T0+7=T1 | 2019-10-10 | 2019-10-17
3 | Setting up of Project Management Unit | Required for overall management of eOffice & SPARROW implementation at user department |  | User Department | T1+1=T2 | T2+7=T3 | 2019-10-18 | 2019-10-25
4 | Orientation Programme | To discuss: a) Roles and responsibilities of each stakeholder b) Implementation Timelines | a) Governance Structure must be in place b) All officers nominated in Governance Structure must attend the Orientation programme c) Project Management Unit must be in place | User Department | T3+1=T4 | T4 | 2019-10-18 | 2019-10-18
5 | Master Data Preparation, Collection and Submission | Required for configuration of eOffice instance according to department's use | a) Data Management, On-site Support and Helpdesk Unit must be in place | User Department | T4 | T4+20=T5 | 2019-10-18 | 2019-11-07
5.1 | Employee Master Details (EMD) | Required for capturing organization and employee data
5.2 | File Heads | Required for capturing Basic, Primary, Secondary & Tertaiary Head used in organization for opening of file
5.3 | Infra-proficiency | Required for generation of infra-gap assessment report (Basically the gaps in infra at client end - Workstation, Scanners, Digital Signature Certificates, etc.)
6 | Master Data Vetting | To intimate the user department regarding the amendments required in master data templates. | a) Master Data Templates must be filled by user department in standardized formats | NIC eOffice Project Division | T5 | T5+7=T6 | 2019-11-07 | 2019-11-14
7 | Master Data Standardization | To ensure that the details provided by user department in master data templates are correct. |  | User Department + NIC eOffice Project Division | T6 | T6+3=T7 | 2019-11-14 | 2019-11-17
8 | Instance Set Up | a) eOffice Environment Setup at data centre b) Customization and Configuration according to department's use | a) Deployment Infrastructure (vCPU, RAM, Storage, etc.) at Data centre must be in place | NIC eOffice Project Division | T4 | T4+7=T8 | 2019-10-18 | 2019-10-25
9 | IGAR Generation, Procurement Initiation & Completion | Required for generation of infra-gap assessment report (Basically the gaps in infra at client end - Workstation, Scanners, Digital Signature Certificates, etc.) | a) Infra-proficiency template must be filled by the department in standardized format | NIC eOffice Project Division | T5 | T5+30=T9 | 2019-11-07 | 2019-12-07
10 | Transition & Digitization Strategy Finalization | Required for preparation of transition plan and scanning of legacy files, active files, inward and outward correspondence | a) Digitization, Diary and Disptach Unit must be in place | User Department | T4 | T4+10=T10 | 2019-10-18 | 2019-10-28
11 | Training Schedule Submission | Submission of training calendar by user department | a) Capacity Building Unit must be in place | User Department | T7 | T7+7=T11 | 2019-11-17 | 2019-11-24
11.1 | EMD Managers | EMD Managers are responsible for: a) updation of organization and employee data b) responsible for interdepartmental transfer and postings c) assigning roles and privileges
11.2 | Master Trainers | Master Trainers are responsbile for: a) providing training to end users after getting trained by NIC eOffice Team.
11.3 | Users | Master Trainers will provide training on eOffice to end users.
PHASE II: PREPARATION
S.No. | Activities | Purpose | Pre-cursor Activities | Responsibility | Start Date | End Date | Start Date | End Date
12 | Training Programme -I | Providing training on eOffice to EMD Managers so that they can populate the standardized EMD & File Heads data into eOffice through front end applications and further perform their responsbilities as mentioned at Point 10.1 above | a) Capacity Building Unit must be in place | NIC eOffice Project Division | T11+1=T12 | T12+5=T13 | 2019-11-25 | 2019-11-30
12.1 | EMD Managers
13 | Master Data Population | Population of Master Data (EMD & File Heads) through front end applications so that application can be configured according to department's use. | a) Training on eOffice has been provided to EMD Managers | User Department | T13+1=T14 | T14+10=T15 | 2019-12-01 | 2019-12-11
14 | Test Migration of OPA/FTS/DMIS (if available) to eOffice | NIC will migrate the data from OPA/FTS/DMIS application (developed by NIC-eOffice or NIC-DoPT Team) to eOffice and access of eOffice will be provided to user department to vet the migrated data. | a) User Department will provide backup of OPA / FTS / DMIS application (in case it is hosted at Local Data Centre / State Data Centre) to NIC. | User Department + NIC eOffice Project Division | T15+1=T16 | T16+10=T17 | 2019-12-12 | 2019-12-22
15 | DSC Registration | Registration of DSC with application for digitally signing notings & drafts | a) DSC are procured | User Department | T17+1=T18 | T18+10=T19 | 2019-12-23 | 2020-01-02
16 | Training Programme -II | Providing training on eOffice to Master Trainers so that they can further impart training to end users of the department. | a) Capacity Building Unit must be in place | User Department + NIC eOffice Project Division | T19+1=T20 | T20+20=T21 | 2020-01-03 | 2020-01-23
16.1 | Master Trainers
16.2 | End Users
PHASE III: IMPLEMENTATION
S.No. | Activities | Purpose | Pre-cursor Activities | Responsibility | Start Date | End Date | Start Date | End Date
17 | Trial Run | During this time users have a fair knowledge of application. Trail basis files and receipts may be generated from top to bottom to complete a loop for testing. | All the aforesaid activities along with Pre-cursour activities must be in place | User Department | T21+1=T22 | T22+7=T23 | 2020-01-24 | 2020-01-31
18 | OPA/FTS/DMIS Stoppage and Final Migration of OPA/FTS/DMIS into eOffice | OPA/FTS/DMIS application running at user department will be stopped and final migration of OPA/FTS/DMIS application will be done by NIC. |  | User Department + NIC eOffice Project Division | T23+1=T24 | T24+5=T25 | 2020-02-01 | 2020-02-06
19 | Go Live | From this date onwards, the application does live and all the previous trial data generated in the application is deleted. |  | User Department | T25+1=T26 |  | 2020-02-07
Formulas:
End Date = [Fill Start Date]
End Date = [Fill Start Date]+7
Fill Start Date = [End Date, row above]
Fill Start Date = [End Date, row above]+1

## Summary
Activities involved in implementation of eOffice and SPARROW at User Department
Rollout of eOffice and SPARROW requires various preliminary activities that are of paramount importance. This includes the requirements of infrastructure at client side and server side, Continuous Capacity Building and hand-holding, Helpdesk Support, etc. All these activities must be in place for smooth & successful implementation of eOffice & SPARROW and their sustainability.
S.No. | Activity / Item | Description
1 | Requirements at Client Side | Infrastructure requirements at User Department for implementation of eOffice & SPARROW
1.1 | Workstation (Desktops / Laptops) | Required by each eOffice & SPARROW user for accessing eOffice & SPARROW application
1.2 | Scanners | Required at each DAK Entry Point for scanning inward correspondence
1.3 | Digital Signature Certificates (DSC) | Required for signing notings & drafts in electronic files in eOffice and APARs in SPARROW
2 | Setting up of Units | Setting up of different units at User Department for implementation of eOffice & SPARROW
2.1 | Digitization, Diary and Disptach Unit | Required for digitization of legacy files and inward correspondence. And also for diarization of inward correspondence & issuing of outward correspondence.
2.2 | Capacity Building Unit | Required for providing training on eOffice & SPARROW and working knowledge on computer system and Internet Browsing to eOffice and SPARROW users.
2.3 | Data Management, On-site Support and Helpdesk Unit | Required for master data preparation (Organization & Employee Data, File Heads, Subject Category, etc.) and management (Creation of New Employee, Retirement, Transfer, etc.) in eOffice & SPARROW instance. Providing On-site and Helpdesk support to eOffice and SPARROW users.
2.4 | Project Management Unit | Required for overall administration and management of eOffice and SPARROW implementation at user department
3 | eOffice & SPARROW Procurement Cost | Cost to be borne by user department for procurement of eOffice & SPARROW
3.1 | Product Enhancement and Maintenance Cost | Required for developing new functionalities, new reports, changes in existing components, testing, security audit and copyright of applications.
3.2 | Operations & Core Roll Out Components Cost | Required for providing eOffice & SPARROW applications deployment support, Capacity Building, Offline support through email & telephone, latest releases, etc. to the user department for a period of five years.
4 | Deployment Infrastructure Cost | Cost to be borne by user department for deployment of eOffice & SPARROW at data centre
4.1 | Deployment Procurement Cost - eOffice | Required for provisioning of hardware (Servers, SAN Storage, etc.), Software (Operating System ,etc.), SSL Certificate, DNS Registration, SMS & Email Gateway, eSign facility, etc. at data centre for hosting of eOffice & SPARROW Product.
4.2 | Deployment Procurement Cost - SPARROW

## Requirements at Client Side
REQUIREMENTS AT CLIENT SIDE
S.No. | Item | Desciption | Minimum Specifications
1 | Workstation (Desktop / Laptop) | Required by each eOffice & SPARROW user for accessing eOffice & SPARROW application | Processor: 2 GHz and above
RAM: 2 GB and above
Operating System: Windows 7 or above
Browser: Internet Explorer (Latest version), Mozilla Firefox (Latest version)
Adobe Reader (Latest version)
2 | Scanners | Required at each DAK Entry Point for scanning inward correspondence | Type | Medium | High
|  |  | Document feeding | Automatic document feeding
|  |  | Document size | Width: 50.8 - 216mm, Length: 53.9 - 356mm
|  |  | Feeding capacity | Up to 50 sheets of good quality paper or up to 4.8mm high (maximum) Legal, A4 and A3
|  |  | Scanning side | Simplex / Duplex, Single pass duplex scan facility preferable
|  |  | Scanning speed | 50 ppm | 100 ppm
|  |  | Scanning modes | Black and White, 256-level Grayscale, 24-bit Colour
|  |  | Scanning resolutions | 100 x 100dpi, 150 x 150dpi, 200 x 200dpi, 300 x 300dpi, 400 x 400dpi, 600 x 600dpi
|  |  | Scanning output | Able to scan into pdf
3 | Digital Signature Certificates (DSC) | Required for signing notings & drafts in electronic files in eOffice and APARs in SPARROW | Class 2 or above DSC with Signing Certificate
For Gap Analysis at Client Side, Click Here

## Setting up of Units
SETTING UP OF UNITS
S.No. | Unit Name | Required for | Requirements | Assumptions
1 | Digitization, Diary and Dispatch Unit | Required for digitization of legacy files and inward correspondence. And also for the diarization of inward correspondence and issuing of outward correspondence | No. of Pages to be scanned in legacy files (Hiring of Digitization Agency) | a) Space for setting up of Digitization, Diary and Disptach Unit is in place
Workstations (Desktops/ Laptops)
Scanners
Manpower Resources
3 | Capacity Building Unit | Required for providing training on eOffice & SPARROW and working knowledge on computer system and Internet Browsing to eOffice and SPARROW users. | Workstations (Desktops/ Laptops) | a) Space for setting up of Capacity Building Unit is in place for atleast 20 users b) Projector with display screen are in place
Scanners
Manpower Resources
4 | Data Management, On-site Support and Helpdesk Unit | Required for master data preparation (Organization & Employee Data, File Heads, Subject Category, etc.) and management (Creation of New Employee, Retirement, Transfer, etc.) in eOffice & SPARROW instance. Providing On-site and Helpdesk support to eOffice and SPARROW users. | Workstations (Desktops/ Laptops) | a) Space for setting up of Data Management, On-site Support and Helpdesk Unit is in place b) Telephone Connection is in place
Manpower Resources
4 | Project Management Unit | Required for overall administration and management of eOffice and SPARROW implementation at user department | Workstations (Desktops/ Laptops) | a) Space for setting up of Project Management Unit is in place b) Telephone Connection is in place
Manpower Resources

## Operations Cost
COST FOR IMPLEMENTATION OF EOFFICE AND SPARROW
Costing Heads |  | User Base in Slabs
| 0 | 0-100 | 101-250 | 251-500 | 501-1000 | 1001-5000 | 5001-10000 | 10001-25000 | 25001-50000
Activity |  | (in Lakhs)
Product Enhancement and Maintenance Cost | 0 | 550000 | 770000 | 1210000 | 1650000 | 2200000 | 2200000 | 2200000 | 2200000
Operations and Core Roll Out Components | 0 | 330000 | 550000 | 990000 | 1210000 | 1650000 | 1980000 | 2376000 | 2851200
TOTAL COST | 0 | 880000 | 1320000 | 2200000 | 2860000 | 3850000 | 4180000 | 4576000 | 5051200
(Taxes Extra)
Product Enhancement and Maintenance Cost |  |  |  | Operations and Core Roll Out Components
• Design and Development of new modules, features |  |  |  | • eOffice Applications deployment support
• Customisation & Configuration |  |  |  | • Core Central Admin for Release Management and patch updates
• Migration of OPA/FTS/DMIS application (developed by NIC-eOffice or NIC-DoPT Team) |  |  |  | • Core Work Bench for Project Implementation Management and Training
• Testing |  |  |  | • Preparation of User Manuals & eLearning Tools
• Security and Quality Audit |  |  |  | • Programme Management Unit
• Copyright process |  |  |  | • Travel (local and outstation)
• Documentation |  |  |  | • Contingencies
• Software for Development |  |  |  | • Promotional Activities
• Development Seat Cost |  |  |  | • Helpdesk Support

## Deployment Infra-eOffice
DEPLOYMENT INFRASTRUCTURE REQUIREMENTS - EOFFICE AT PRIMARY DATA CENTRE (MANDATORY)
S.No. | Server Type |  | User Base in Slabs
|  |  | 0-100 |  |  | 101-250 |  |  | 251-500 |  |  | 501-1000 |  |  | 1001-5000 |  |  | 5001-10000 |  |  | 10001-25000 |  |  | 25001-50000
|  |  | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB)
1 | Database Server |  | 12 | 16 | 100 | 20 | 24 | 100 | 24 | 32 | 200 | 28 | 48 | 200 | 32 | 64 | 300 | 40 | 96 | 400 | 48 | 128 | 500 | 64 | 256 | 500
2 | Logical Replication (DB) Server |  | 6 | 8 | 100 | 10 | 12 | 100 | 12 | 16 | 200 | 14 | 24 | 200 | 16 | 32 | 300 | 20 | 48 | 400 | 24 | 64 | 500 | 32 | 128 | 500
3 | DB SR Server |  | 2 | 4 | 300 | 4 | 6 | 300 | 4 | 8 | 600 | 6 | 12 | 600 | 8 | 16 | 900 | 8 | 20 | 1200 | 12 | 24 | 1500 | 16 | 32 | 1500
4 | Web Server |  | 4 | 8 | 0 | 4 | 8 | 0 | 4 | 8 | 0 | 4 | 8 | 0 | 8 | 16 | 0 | 8 | 16 | 0 | 12 | 24 | 0 | 16 | 32 | 0
5 | Application Server 1 |  | 8 | 24 | 400 | 12 | 24 | 500 | 12 | 40 | 600 | 16 | 56 | 800 | 12 | 40 | 100 | 16 | 48 | 100 | 20 | 56 | 100 | 20 | 64 | 100
6 | Application Server 2 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12 | 40 | 1100 | 16 | 48 | 2100 | 20 | 56 | 100 | 20 | 64 | 100
7 | Application Server 3 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 56 | 4100 | 20 | 64 | 100
8 | Application Server 4 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 64 | 100
9 | Application Server 5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 64 | 8100
10 | CRL Server |  | 2 | 4 | 50 | 2 | 4 | 50 | 2 | 4 | 50 | 2 | 4 | 50 | 4 | 8 | 50 | 4 | 8 | 50 | 4 | 8 | 50 | 4 | 8 | 50
11 | Application Failover / Backup Server |  | 2 | 4 | 450 | 2 | 4 | 550 | 2 | 4 | 650 | 2 | 4 | 850 | 4 | 8 | 1150 | 4 | 8 | 2150 | 4 | 8 | 4150 | 4 | 8 | 8150
12 | Logs Server |  | 2 | 2 | 50 | 2 | 2 | 100 | 2 | 2 | 150 | 2 | 2 | 300 | 4 | 8 | 1500 | 4 | 8 | 3000 | 4 | 8 | 7500 | 4 | 8 | 15000
13 | Logs Backup Server |  | 2 | 2 | 50 | 2 | 2 | 100 | 2 | 2 | 150 | 2 | 2 | 300 | 4 | 8 | 1500 | 4 | 8 | 3000 | 4 | 8 | 7500 | 4 | 8 | 15000
DEPLOYMENT INFRASTRUCTURE REQUIREMENTS - EOFFICE AT REMOTE DATA CENTRE (STRONGLY RECOMMENDED)
S.No. | Server Type |  | User Base in Slabs
|  |  | 0-100 |  |  | 101-250 |  |  | 251-500 |  |  | 501-1000 |  |  | 1001-5000 |  |  | 5001-10000 |  |  | 10001-25000 |  |  | 25001-50000
|  |  | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB)
1 | DB SR Server |  | 2 | 4 | 300 | 4 | 6 | 300 | 4 | 8 | 600 | 6 | 12 | 600 | 8 | 16 | 900 | 8 | 20 | 1200 | 12 | 24 | 1500 | 16 | 32 | 1500
2 | Backup Server |  | 2 | 4 | 450 | 2 | 4 | 550 | 2 | 4 | 650 | 2 | 4 | 850 | 4 | 8 | 1150 | 4 | 8 | 2150 | 4 | 8 | 4150 | 4 | 8 | 8150
3 | Logs Backup Server |  | 2 | 2 | 50 | 2 | 2 | 100 | 2 | 2 | 150 | 2 | 2 | 300 | 4 | 8 | 1500 | 4 | 8 | 3000 | 4 | 8 | 7500 | 4 | 8 | 15000
DEPLOYMENT INFRASTRUCTURE COST - EOFFICE AT PRIMARY DATA CENTRE (MANDATORY)
S.No. | Server Type |  | User Base in Slabs
|  | 0 | 0-100 |  | 101-250 |  | 251-500 |  | 501-1000 |  | 1001-5000 |  | 5001-10000 |  | 10001-25000 |  | 25001-50000
1 | Database Server | 0 | 21392 |  | 31944 |  | 40970 |  | 48430 |  | 58912 |  | 76854 |  | 94796 |  | 136284
2 | Logical Replication (DB) Server | 0 | 13114 |  | 18390 |  | 24414 |  | 28144 |  | 34896 |  | 45378 |  | 55860 |  | 76604
3 | DB SR Server | 0 | 13882 |  | 16520 |  | 25950 |  | 28952 |  | 41020 |  | 50814 |  | 65156 |  | 71160
4 | Web Server |  | 7818 |  | 7818 |  | 7818 |  | 7818 |  | 13822 |  | 13822 |  | 19826 |  | 25830
5 | Application Server 1 | 0 | 27366 |  | 34936 |  | 40870 |  | 54374 |  | 25760 |  | 31764 |  | 37768 |  | 39224
6 | Application Server 2 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | 55980 |  | 92204 |  | 37768 |  | 39224
7 | Application Server 3 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 158648 |  | 39224
8 | Application Server 4 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 39224
9 | Application Server 5 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 280984
10 | CRL Server |  | 6327 |  | 6327 |  | 6327 |  | 6327 |  | 9329 |  | 9329 |  | 9329 |  | 9329
11 | Application Failover / Backup Server |  | 18415 |  | 21437 |  | 24459 |  | 30503 |  | 42571 |  | 72791 |  | 133231 |  | 254111
12 | Logs Server |  | 5963 |  | 7474 |  | 8985 |  | 13518 |  | 53148 |  | 98478 |  | 234468 |  | 461118
13 | Logs Backup Server |  | 5963 |  | 7474 |  | 8985 |  | 13518 |  | 53148 |  | 98478 |  | 234468 |  | 461118
Cost for One Month |  | 0 | 120240 |  | 152320 |  | 188778 |  | 231584 |  | 388586 |  | 589912 |  | 1081318 |  | 1933434
Cost for Three Years |  | 0 | 4328640 |  | 5483520 |  | 6796008 |  | 8337024 |  | 13989096 |  | 21236832 |  | 38927448 |  | 69603624
Cost for Five Years |  | 0 | 7214400 |  | 9139200 |  | 11326680 |  | 13895040 |  | 23315160 |  | 35394720 |  | 64879080 |  | 116006040
DEPLOYMENT INFRASTRUCTURE COST - EOFFICE AT REMOTE DATA CENTRE (STRONGLY RECOMMENDED)
S.No. | Server Type |  | User Base in Slabs
|  | 0 | 0-100 |  | 101-250 |  | 251-500 |  | 501-1000 |  | 1001-5000 |  | 5001-10000 |  | 10001-25000 |  | 25001-50000
1 | DB SR Server | 0 | 13882 |  | 16520 |  | 25950 |  | 28952 |  | 41020 |  | 50814 |  | 65156 |  | 71160
2 | Backup Server |  | 18415 |  | 21437 |  | 24459 |  | 30503 |  | 42571 |  | 72791 |  | 133231 |  | 254111
3 | Logs Backup Server |  | 5963 |  | 7474 |  | 8985 |  | 13518 |  | 53148 |  | 98478 |  | 234468 |  | 461118
Cost for One Month |  | 0 | 38260 |  | 45431 |  | 59394 |  | 72973 |  | 136739 |  | 222083 |  | 432855 |  | 786389
Cost for Three Years |  | 0 | 1377360 |  | 1635516 |  | 2138184 |  | 2627028 |  | 4922604 |  | 7994988 |  | 15582780 |  | 28310004
Cost for Five Years |  | 0 | 2295600 |  | 2725860 |  | 3563640 |  | 4378380 |  | 8204340 |  | 13324980 |  | 25971300 |  | 47183340
TOTAL DEPLOYMENT INFRASTRUCTURE COST - EOFFICE AT BOTH PRIMARY DATA CENTRE AND REMOTE DATA CENTRE
S.No. | Duration |  | User Base in Slabs
|  | 0 | 0-100 |  | 101-250 |  | 251-500 |  | 501-1000 |  | 1001-5000 |  | 5001-10000 |  | 10001-25000 |  | 25001-50000
1 | Cost for One Month | 0 | 158500 |  | 197751 |  | 248172 |  | 304557 |  | 525325 |  | 811995 |  | 1514173 |  | 2719823
2 | Cost for Three Years |  | 5706000 |  | 7119036 |  | 8934192 |  | 10964052 |  | 18911700 |  | 29231820 |  | 54510228 |  | 97913628
3 | Cost for Five Years |  | 9510000 |  | 11865060 |  | 14890320 |  | 18273420 |  | 31519500 |  | 48719700 |  | 90850380 |  | 163189380
Approved Rates for NIC Cloud Services - PaaS Model (w.e.f. 24.08.2016) | [9 empty] | Additional Activities to be undertaken by NIC in case eOffice instance is hosted in eOffice Cloud at National Data Centre, Shastri Park
S.No. | Description |  |  |  |  | Approved Rate (in Rs.) per month |  |  |  | S.No. | Activity |  |  |  | Required for
1 | VM of 1 vCPU, 1 GB RAM, 60 GB Storage per month |  |  |  |  | 3133 |  |  |  | 1 | eSign Facility |  |  |  | Required for signing notings & drafts in electronic files in eOffice and APARs in SPARROW
2 | Additional cost of per 1vCPU per month |  |  |  |  | 1137 |  |  |  | 2 | SSL Certificate |  |  |  | Required for client server connection encryption and also for single sign-on (CAS) purpose
3 | Additional cost of per 1 GB RAM per month |  |  |  |  | 182 |  |  |  | 3 | DNS Registration |  |  |  | Required for accessing the eOffice & SPARROW instance by name rather than IP
4 | Additional cost of per 50 GB Storage Space per month |  |  |  |  | 1511 |  |  |  | 4 | NIC / GOI Email IDs Creation |  |  |  | Required for login & authenticate in eOffice & SPARROW instance
[10 empty] | 5 | SMS and Email Gateway |  |  |  | Required for alert services

## Deployment Infra-SPARROW
DEPLOYMENT INFRASTRUCTURE REQUIREMENTS - SPARROW AT PRIMARY DATA CENTRE (MANDATORY)
S.No. | Server Type |  | User Base in Slabs
|  |  | 0-100 |  |  | 101-250 |  |  | 251-500 |  |  | 501-1000 |  |  | 1001-5000 |  |  | 5001-10000 |  |  | 10001-25000 |  |  | 25001-50000
|  |  | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB)
1 | Database Server |  | 4 | 8 | 100 | 6 | 16 | 100 | 8 | 20 | 200 | 12 | 24 | 200 | 16 | 32 | 400 | 24 | 64 | 400 | 32 | 96 | 1000 | 48 | 128 | 1000
2 | DB SR Server |  | 4 | 8 | 300 | 4 | 8 | 300 | 6 | 12 | 600 | 8 | 12 | 600 | 12 | 16 | 1000 | 16 | 24 | 1200 | 24 | 32 | 2500 | 24 | 64 | 3000
3 | Web Server |  | 2 | 4 | 0 | 2 | 4 | 0 | 2 | 4 | 0 | 4 | 8 | 0 | 4 | 8 | 0 | 8 | 16 | 0 | 12 | 24 | 0 | 16 | 48 | 0
4 | Application Server 1 |  | 6 | 12 | 200 | 10 | 16 | 200 | 14 | 20 | 350 | 12 | 24 | 350 | 20 | 40 | 400 | 20 | 40 | 100 | 28 | 56 | 100 | 28 | 52 | 100
5 | Application Server 2 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 40 | 1000 | 28 | 56 | 100 | 28 | 52 | 100
6 | Application Server 3 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28 | 56 | 1600 | 28 | 52 | 100
7 | Application Server 4 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28 | 52 | 2600
8 | CRL Server |  | 2 | 4 | 50 | 2 | 4 | 50 | 2 | 4 | 50 | 2 | 4 | 50 | 4 | 8 | 50 | 4 | 8 | 50 | 4 | 8 | 50 | 4 | 8 | 50
9 | Application Failover / Backup Server |  | 2 | 4 | 250 | 2 | 4 | 250 | 2 | 4 | 400 | 2 | 4 | 400 | 4 | 8 | 450 | 4 | 8 | 1050 | 4 | 8 | 1650 | 4 | 8 | 2650
10 | Logs Server |  | 2 | 2 | 50 | 2 | 2 | 100 | 2 | 2 | 150 | 2 | 2 | 250 | 4 | 8 | 1300 | 4 | 8 | 2500 | 4 | 8 | 6500 | 4 | 8 | 13000
11 | Logs Backup Server |  | 2 | 2 | 50 | 2 | 2 | 100 | 2 | 2 | 150 | 2 | 2 | 250 | 4 | 8 | 1300 | 4 | 8 | 2500 | 4 | 8 | 6500 | 4 | 8 | 13000
DEPLOYMENT INFRASTRUCTURE REQUIREMENTS - SPARROW AT REMOTE DATA CENTRE (STRONGLY RECOMMENDED)
S.No. | Server Type |  | User Base in Slabs
|  |  | 0-100 |  |  | 101-250 |  |  | 251-500 |  |  | 501-1000 |  |  | 1001-5000 |  |  | 5001-10000 |  |  | 10001-25000 |  |  | 25001-50000
|  |  | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB) | Cores | RAM (in GB) | Storage (in GB)
1 | DB SR Server |  | 4 | 8 | 300 | 4 | 8 | 300 | 6 | 12 | 600 | 8 | 12 | 600 | 12 | 16 | 1000 | 16 | 24 | 1200 | 24 | 32 | 2500 | 24 | 64 | 3000
2 | Backup Server |  | 2 | 4 | 250 | 2 | 4 | 250 | 2 | 4 | 400 | 2 | 4 | 400 | 4 | 8 | 450 | 4 | 8 | 1050 | 4 | 8 | 1650 | 4 | 8 | 2650
3 | Logs Backup Server |  | 2 | 2 | 50 | 2 | 2 | 100 | 2 | 2 | 150 | 2 | 2 | 250 | 4 | 8 | 1300 | 4 | 8 | 2500 | 4 | 8 | 6500 | 4 | 8 | 13000
DEPLOYMENT INFRASTRUCTURE COST - SPARROW AT PRIMARY DATA CENTRE (MANDATORY)
S.No. | Server Type |  | User Base in Slabs
|  | 0 | 0-100 |  | 101-250 |  | 251-500 |  | 501-1000 |  | 1001-5000 |  | 5001-10000 |  | 10001-25000 |  | 25001-50000
1 | Database Server | 0 | 10840 |  | 14570 |  | 20594 |  | 25870 |  | 37918 |  | 52838 |  | 85890 |  | 109906
2 | DB SR Server | 0 | 16884 |  | 16884 |  | 28952 |  | 31226 |  | 48590 |  | 60638 |  | 110476 |  | 131410
3 | Web Server |  | 4816 |  | 4816 |  | 4816 |  | 7818 |  | 7818 |  | 13822 |  | 19826 |  | 28742
4 | Application Server 1 | 0 | 16864 |  | 22140 |  | 31949 |  | 30403 |  | 43922 |  | 34856 |  | 46864 |  | 46136
5 | Application Server 2 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 62054 |  | 46864 |  | 46136
6 | Application Server 3 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 92194 |  | 46136
7 | Application Server 4 | 0 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 121686
8 | CRL Server |  | 6327 |  | 6327 |  | 6327 |  | 6327 |  | 9329 |  | 9329 |  | 9329 |  | 9329
9 | Application Failover / Backup Server |  | 12371 |  | 12371 |  | 16904 |  | 16904 |  | 21417 |  | 39549 |  | 57681 |  | 87901
10 | Logs Server |  | 5963 |  | 7474 |  | 8985 |  | 12007 |  | 47104 |  | 83368 |  | 204248 |  | 400678
11 | Logs Backup Server |  | 5963 |  | 7474 |  | 8985 |  | 12007 |  | 47104 |  | 83368 |  | 204248 |  | 400678
Cost for One Month |  | 0 | 80028 |  | 92056 |  | 127512 |  | 142562 |  | 263202 |  | 439822 |  | 877620 |  | 1428738
Cost for Three Years |  | 0 | 2881008 |  | 3314016 |  | 4590432 |  | 5132232 |  | 9475272 |  | 15833592 |  | 31594320 |  | 51434568
Cost for Five Years |  | 0 | 4801680 |  | 5523360 |  | 7650720 |  | 8553720 |  | 15792120 |  | 26389320 |  | 52657200 |  | 85724280
DEPLOYMENT INFRASTRUCTURE COST - SPARROW AT REMOTE DATA CENTRE (STRONGLY RECOMMENDED)
S.No. | Server Type |  | User Base in Slabs
|  | 0 | 0-100 |  | 101-250 |  | 251-500 |  | 501-1000 |  | 1001-5000 |  | 5001-10000 |  | 10001-25000 |  | 25001-50000
1 | DB SR Server | 0 | 16884 |  | 16884 |  | 28952 |  | 31226 |  | 48590 |  | 60638 |  | 110476 |  | 131410
2 | Backup Server |  | 12371 |  | 12371 |  | 16904 |  | 16904 |  | 21417 |  | 39549 |  | 57681 |  | 87901
3 | Logs Backup Server |  | 5963 |  | 7474 |  | 8985 |  | 12007 |  | 47104 |  | 83368 |  | 204248 |  | 400678
Cost for One Month |  | 0 | 35218 |  | 36729 |  | 54841 |  | 60137 |  | 117111 |  | 183555 |  | 372405 |  | 619989
Cost for Three Years |  | 0 | 1267848 |  | 1322244 |  | 1974276 |  | 2164932 |  | 4215996 |  | 6607980 |  | 13406580 |  | 22319604
Cost for Five Years |  | 0 | 2113080 |  | 2203740 |  | 3290460 |  | 3608220 |  | 7026660 |  | 11013300 |  | 22344300 |  | 37199340
TOTAL DEPLOYMENT INFRASTRUCTURE COST - SPARROW AT BOTH PRIMARY DATA CENTRE AND REMOTE DATA CENTRE
S.No. | Duration |  | User Base in Slabs
|  | 0 | 0-100 |  | 101-250 |  | 251-500 |  | 501-1000 |  | 1001-5000 |  | 5001-10000 |  | 10001-25000 |  | 25001-50000
1 | Cost for One Month | 0 | 115246 |  | 128785 |  | 182353 |  | 202699 |  | 380313 |  | 623377 |  | 1250025 |  | 2048727
2 | Cost for Three Years |  | 4148856 |  | 4636260 |  | 6564708 |  | 7297164 |  | 13691268 |  | 22441572 |  | 45000900 |  | 73754172
3 | Cost for Five Years |  | 6914760 |  | 7727100 |  | 10941180 |  | 12161940 |  | 22818780 |  | 37402620 |  | 75001500 |  | 122923620
Approved Rates for NIC Cloud Services - PaaS Model (w.e.f. 24.08.2016) | [9 empty] | Additional Activities to be undertaken by NIC in case SPARROW instance is hosted in eOffice Cloud at National Data Centre, Shastri Park
S.No. | Description |  |  |  |  | Approved Rate (in Rs.) per month |  |  |  | S.No. | Activity |  |  |  | Required for
1 | VM of 1 vCPU, 1 GB RAM, 60 GB Storage per month |  |  |  |  | 3133 |  |  |  | 1 | eSign Facility |  |  |  | Required for signing notings & drafts in electronic files in eOffice and APARs in SPARROW
2 | Additional cost of per 1vCPU per month |  |  |  |  | 1137 |  |  |  | 2 | SSL Certificate |  |  |  | Required for client server connection encryption and also for single sign-on (CAS) purpose
3 | Additional cost of per 1 GB RAM per month |  |  |  |  | 182 |  |  |  | 3 | DNS Registration |  |  |  | Required for accessing the eOffice & SPARROW instance by name rather than IP
4 | Additional cost of per 50 GB Storage Space per month |  |  |  |  | 1511 |  |  |  | 4 | NIC / GOI Email IDs Creation |  |  |  | Required for login & authenticate in eOffice & SPARROW instance
[10 empty] | 5 | SMS and Email Gateway |  |  |  | Required for alert services

## Manpower Resources
NIC RECOMMENDATIONS ON HIRING OF MANPOWER RESOURCES FOR ROLLOUT OF EOFFICE & SPARROW AT USER DEPARTMENT
Note: The figures provided below are only general and indicative figures w.r.t. deployment of manpower at a single location that may help user department to estimate their resources, however, it is suggested that user department may also further estimate the requirements based on their local needs / geographical locations etc.
S.No. | Name of Unit | Required for | Resource Category | 0 | 0-100 | 101-250 | 251-500 | 501-1000 | 1001-5000 | 5001-10000 | 10001-25000 | 25001-50000
Number of Resources per location
1 | Digitization, Diary and Dispatch Unit | Required for digitization of legacy files and inward correspondence. And also for the diarization of inward correspondence and issuing of outward correspondence | Project Lead | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 4
|  |  | Project Engineer | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 4
Total |  |  |  | 0 | 2 | 2 | 3 | 3 | 3 | 4 | 6 | 8
2 | Capacity Building Unit | Required for providing training on eOffice & SPARROW and working knowledge on computer system and Internet Browsing to eOffice and SPARROW users. | Project Lead | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 4
|  |  | Project Engineer | 0 | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 6
Total |  |  |  | 0 | 2 | 2 | 3 | 3 | 4 | 6 | 8 | 10
3 | Data Management, On-site Support and Helpdesk Unit | Required for master data preparation (Organization & Employee Data, File Heads, Subject Category, etc.) and management (Creation of New Employee, Retirement, Transfer, etc.) in eOffice & SPARROW instance. Providing On-site and Helpdesk support to eOffice and SPARROW users. | Project Lead | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5
|  |  | Project Engineer | 0 | 2 | 2 | 2 | 3 | 4 | 7 | 9 | 11
Total |  |  |  | 0 | 3 | 3 | 4 | 5 | 7 | 10 | 13 | 16
4 | Project Management Unit | Required for overall administration and management of eOffice and SPARROW implementation at user department | Project Manager | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Project Lead | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2
|  |  | Project Engineer | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
Total |  |  |  | 0 | 2 | 2 | 3 | 4 | 4 | 4 | 5 | 5
5 | System Administration | Required for administering, managing and maintaining the eOffice and SPARROW instance of user department. They will also deploy latest patches / updates whenever provided by NIC eOffice Team. | Technical Manager | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2
|  |  | Deployment Lead | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3
|  |  | Deployment Engineer | 0 | 1 | 1 | 1 | 1 | 2 | 3 | 4 | 5
Total |  |  |  | 0 | 2 | 2 | 2 | 3 | 4 | 6 | 8 | 10
GRAND TOTAL |  |  |  | 0 | 11 | 11 | 15 | 18 | 22 | 30 | 40 | 49

## Indicative Work Profiles
INDICATIVE WORK PROFILE / SKILL SET OF MANPOWER RESOURCES TO BE DEPLOYED IN EACH UNIT FOR ROLLOUT OF EOFFICE & SPARROW AT USER DEPARTMENT
S.No. | Name of Unit | Indicative Work Profile/Skill Set of Manpower Resources Deployed in Unit
1 | Digitization, Diary and Dispatch Unit | a) Assist user department in scanning, digitization and migration activities. b) Ensure that all the papers (notings, receipts, etc.) needs to be scanned as per the standard scanning guidelines provided by eOffice Team. c) Ensure that the meta-data at the time of diarization and dispatch must be filled properly.
2 | Capacity Building Unit | Master Trainers identified/hired by user department may be deputed in this unit. They will be resposible for following: a) Providing continuous training and hand-holding to end users of the department. b) Providing training and hand-holding on new features to the end users of the department, as and when released. c) Planning, scheduling, managing and tracking the training sessions to be held for senior management / users / dealing hands on the application. d) Testing of the new versions and features of eOffice
3 | Data Management, On-site Support and Helpdesk Unit | EMD Managers and On-site Roll Out Team identified/hired by user department may be deputed in this unit. EMD Managers are resposible for following: a) Preparation and Population of eOffice Master Data [Employee Master Details (EMD), File Heads, etc.] into the application b) eOffice user account creation, whenever a new employee joins the organization. c) Managing inter/intra-departmental transfers, promotions, retirement. d) Providing roles and privileges as per the working of the organization. The On-site Roll Out Team and Helpdesk Unit are responsible for following: a) Provide trouble-shooting support to end users facing problems in eOffice. b) Respond to telephone calls and emails received from users looking for help with issues related to eOffice. c) Compiling the list of queries received from users relating to eOffice which are not resolved at their end and escalate them to the Project Management Unit for resolution. d) Testing of the new versions and features of eOffice, as and when released.
4 | Project Management Unit | a) Assist user department in constitution of eOffice Governance Structure b) Assist user department in acquiring Digital Signature Certificates (DSC) / eSign / Email Ids, etc. for all eOffice users c) Assist in setting up of department level Local Help Desk. d) Infrastructure Gap Analysis and Infrastructure readiness e) Regular review meetings with nodal coordinator of user department for smooth, successful and sustainable implementation of eOffice f) Preparation and submission of regular reports on the progress of implementation of eOffice to the eOffice Nodal Coordinator, like number of users on-boarded on eOffice, number of training sessions conducted, number of users trained, number of electronic files / receipts created, etc. g) Providing responses to these queries received from On-site Support and Helpdesk Unit and if needed, escalates the queries to eOffice Team for timely response. h) Liaise among indenting user department, NICSI and other stakeholders in smooth implementation of eOffice system. i) Provide over all guidance to the procuring entity in implementation of the application and share the best practices
5 | System Administration | a) System Administration, Deployment and maintenance of eOffice Product suite in local/state data centre. This also includes the following: i) LDAP Integration ii) Configuration of SMS & Email gateway iii) DNS Binding iv) SSL Configuration b) Linux installation c) LVM configuration and troubleshooting d) Patching & fixing updates of the Linux servers. e) User / Group Administration and System security. f) Installing system software applications and Packages using tar ball, RPM, Yum, Linux Server hardening, and Server Monitoring. g) Creating and Managing cron in the beginning of day and end of day process for different servers. h) Web Hosting through Apache i) Managing Apache/Nginx Web Server, Tomcat Web Server j) Load Balancing (Tomcat cluster and Apache/Nginx web server) k) Application Data Backup and Restore l) Installation of PostgreSQL, Configuration and Tuning m) Administration of PostgreSQL users, replication of master/slave server, access rights & taking regular database backups & restoring them in restored in archival server. n) Knowledge of SQL queries o) Awareness of Virtualization and cloud environment p) Installation of monitoring tools like Nagios/Zabbix server configuration etc. q) Monitor the system and respond immediately for security or usability concerns. r) Administrate infrastructure, including firewalls, databases, malware protection software and other processes. s) Review and analyse application and database logs. t) Ensuring the update of all system software like OS, etc. and implementing advisories from eOffice Division from time to time. u) Time to time VA assessment of the servers.

## Infrastructure
NIC RECOMMENDATIONS ON PROVISIONING OF INFRASTRUCTURE RESOURCES FOR ROLLOUT OF EOFFICE & SPARROW AT USER DEPARTMENT
S.No. | Name of Unit | Category |  | 0 | 0-100 | 101-250 | 251-500 | 501-1000 | 1001-5000 | 5001-10000 | 10001-25000 | 25001-50000
Number of Infrastructure Resources per location
1 | Digitization, Diary and Dispatch Unit | Workstations | Desktop | 0 | 2 | 2 | 3 | 3 | 3 | 4 | 6 | 8
|  |  | Laptop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scanners | High End | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3
|  |  | Medium End | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5
2 | Capacity Building Unit | Workstations | Desktop | 0 | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20
|  |  | Laptop | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2
|  | Scanners | Multifunction | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2
3 | Data Management, On-site Support and Helpdesk Unit | Workstations | Desktop | 0 | 2 | 2 | 3 | 4 | 5 | 8 | 11 | 13
|  |  | Laptop | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3
4 | Project Management Unit | Workstations | Desktop | 0 | 1 | 1 | 2 | 3 | 3 | 3 | 4 | 4
|  |  | Laptop | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | System Administration | Workstations | Desktop | 0 | 1 | 1 | 1 | 2 | 3 | 5 | 6 | 8
|  |  | Laptop | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2

## Gap Assessment
INFRA-ASSESSMENT SHEET
S.No. | Name of Employee | Designation | Section Name | NICNET/NKN/SWAN Connectivity Available | Bandwidth Availability | Maximum Bandwidth usage/day | Working Knowledge of Computer | Workstation Available | Processor | RAM (GB) | Operating System | Class 2 or above DSC Available | Volume of DAK per day | No. of Pages in Legacy Files to be scanned | Scanner Available | Scanner Model | Scanner Assignment
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## GEM LINKS
GEM LINKS
S.No. | Item |  | Reference
1 | Workstations | Desktop
2 |  | Laptop
3 | Scanners | High End
4 |  | Medium End
5 |  | Multi-function
6 | Digital Signature Certificates (DSC) (Two years Certificate validity)
7 | SSL Certificate for both eOffice & SPARROW instance (Applicable for Two Years only)